## Slide 1: SysEng 6196 Systems Engineering Capstone
Dr. Lou Pape
1 – Introduction to the SE Management Plan
(SEMP)

## Slide 2: Introduction and Syllabus Review
Professor - Dr. Lou Pape
  Boeing Assoc Technical Fellow, Boeing Designated Expert, Technical Lead Engineer
  Expert Systems Engineering Professional (INCOSE ESEP)
  See Canvas for details
Syllabus review – See Video Introduction
  Note the University policy regarding plagiarism: http://www.umsystem.edu/ums/rules/collected_rules/programs/ch200/200.010_standard_of_conduct
    “200.010 .B.1.b The term plagiarism includes, but is not limited to: (i) use by paraphrase or direct quotation of the published or unpublished work of another person without fully and properly crediting the author with footnotes, citations or bibliographical reference; (ii) unacknowledged use of materials prepared by another person or agency engaged in the selling of term papers or other academic materials; or (iii) unacknowledged use of original work/material that has been produced through collaboration with others without release in writing from collaborators.”
Communications via Canvas:
  Course: SYS_ENG_6196: SYS ENG CAPSTONE
    Videos of lectures are only available to 1DIS students (except scheduled pre-recordings are available to all students)
Introductions (HW-1): Provide your: Name, profession, professional goals, & specific goals for this class, taken prerequisites?

## Slide 3: Outline: Introduction to SE Management and the SE Management Plan
Course overview
SE Management overview
  What is meant by SE Management?
    How does it relate to Systems Engineering?
    How does it relate to Program Management?
  Review of basic SE concepts
    Definitions
    Life-cycle concepts
  SE Development Models and Standards
SEMP overview and outline
Technical planning overview: what, why, who, how, when, where
SEMP tailoring

## Slide 4: Course Overview
See Syllabus for weekly details
Overall focus is the application of learning from the core curriculum
  Nominal Prerequisites: Sys Eng 6105 (Project Mgt), 6104 (Architecting) (squishy)
  Week 1-7: Systems Engineering Management Plan – Section by section drafts
  Readings: sections of INCOSE SE Handbook (ISEH)
  Homework: draft sections due each week
Midterm – Final version of SEMP incorporating comments - due Week 8
Week 8-15: Process Improvement processes
  Readings: Case Studies and 6- textbook (C6 GBH)
  Homework – draft sections due each week
Final: Process Improvement from Case Study
  Use Case Studies to Describe an Improvement Problem Solution, using the Define, Measure, Analyze, Improve, Control (DMAIC) approach

## Slide 5: What is SE Management?
Systems Engineering Management defines the technical management and related activities required to conceive, develop, produce, deploy, operate, and maintain complex systems so as to satisfy user and acquirer needs
“Systems engineering management is accomplished by integrating three major activities:
  Development phasing that controls the design process and provides baselines that coordinate design efforts
  A systems engineering process that provides a structure for solving design problems and tracking requirements satisfaction flow through the design effort
  Life cycle integration that involves customers in the design process and ensures that the system developed is viable throughout its life” (DAU, “SE Fundamentals”, p. 4)

## Slide 6: SE Management in Context
“Begin with the end in mind” - Covey
Product System
Satisfy User
Need – the goal
Organization System
“SE” the Product System
Enterprise System
“SE” the Organization
System, and the Enterprise
Continuous Improvement
Primary Application of SE Management
Primary Application of SE

## Slide 7: The Essence of SE Management
“If you can’t measure it, you can’t manage it.”
SE Management applies Technical Feedback Control in the application of Systems Engineering
The SE Management Plan provides a basis for measurement
Adapted from Blanchard and Fabrycky, “Systems Engineering and Analysis”, Fourth Edition, Figure 11.1
SE Management
SE
SE Products
Input
Process
Output
Measurement
Decision-Making
Action

## Slide 8: Without SE Management…
FBI Virtual Case File*
$170M project cancelled because of
  Poorly defined and slowly evolving design requirements
  Overly ambitious schedules
  Lack of a plan to guide:
    Hardware purchases
    Network deployments
    Software development
  And others
  *2002 DOJ IG Report, referenced in IEEE Spectrum, September 2005, pp 25-26. http://www.spectrum.ieee.org/sep05/1455 http://spectrum.ieee.org/computing/software/who-killed-the-virtual-case-file

## Slide 9: “Big”  “Complex” Systems
Coliseum, Rome
Rumeli Fortress, Istanbul
Saint Peter's Basilica
Golden Gate Bridge
What kinds of system development can most benefit from SE?
  Technology risk
  Cost/Schedule risk (limited resources)
  Complex interfaces and Subsystem interactions
  No iteration opportunity
  Unclear problem
Focus of SE Management Planning should be on these considerations

## Slide 10: SE Standards*
ISO/IEC/IEEE 15288-2015 – Systems and Software Engineering – Life-Cycle Process
  INCOSE SE Handbook v4 aligned with this standard (Our Text!)
ANSI/EIA-632, Processes for Engineering a System
  Derived from draft MIL-STD-499B
IEEE 1220-2005, Standard for Application and Management of the Systems Engineering Process
  Derived from draft MIL-STD-499B
  Re-published as ISO/IEC 26702:2007, “Systems engineering -- Application and management of the systems engineering process”
  Updated to IEEE/ISO/IEC 24748-4-2016, “International Standard for Systems and Software Engineering -- Life Cycle Management -- Part 4: Systems Engineering Planning”
INCOSE Standards List
  https://www.incose.org/about-systems-engineering/se-standards
  *See Syllabus for add’l Links
Notes: https://www.acq.osd.mil/se/docs/15288-Guide-2017.pdf
https://www.sebokwiki.org/wiki/Systems_Engineering_Standards

## Slide 11: SE Technical Processes
Technical Processes for the engineering of…
  The Product System
  The Product-Development Organization and associated processes
  The Enterprise System (business reengineering and continuous improvement)
Common Systems Engineering Technical Processes (Defense Acquisition Guidebook, 4.3.10 – 4.3.17):
  Requirements definition
  Requirements and functional (logical) analysis
  Architecture Design (solution)
  Implementation (fabrication and procurement)
  Integration
  Verification
  Validation

## Slide 12: DAU DAG 4.3.1
“…As a whole, the SE processes provide a systematic approach focused on providing needed capability to the operational end user. Successful implementation of the SE processes results in an integrated capability solution that is:
  Responsive to the needs of the user
  Balanced among multiple requirements, design considerations, and program costs and schedules
  Able to operate in complex system-of-systems (SoS) environments as required…”
Notes: Defense Acquisition Guidebook - DAG

## Slide 13: Life-cycle phasing of Technical Processes
From US DOD Defense Acquisition University
Note that MS B is PDR
http://sebokwiki.org/wiki/System_Realization Figure 3.

## Slide 14: Technical Management Processes
Technical Management Processes for planning, organizing, monitoring, and controlling resources
  Time
  People and organizations, including suppliers
  Facilities and equipment
  Money
  The system being developed
Common Systems Engineering Management Processes (Defense Acquisition Guidebook, 4.3.2 – 4.3.9):
  Technical planning
  Decision analysis (trade studies)
  Technical assessment (reviews and technical measurement)
  Requirements management
  Risk management
  Configuration management
  Technical data management
  Interface management

## Slide 15: Plans in the Life-Cycle
TEMP
SEP  SEMP
SEPSEMP
Integrated Logistics Plan
SEP: US Gov’t DoD Systems Engineering Plan
The SEMP or SEP is THE technical management plan for the program
Not limited to SEs
From US DODI 5000.02, 1/2015
Figure 3, Model 1: Hardware Intensive Program http://www.acq.osd.mil/fo/docs/500002p.pdf
From Blanchard, “System Engineering Management”, 4th Edition
Notes: DODI 5000.02 is the biggy on how to develop systems

## Slide 16: SEMP Overview
Purposes
  Identify the system to be managed (“SE the SEMP”)
    Use the unmanned urban vehicle or any equivalent project from 5101 [368], 6102 [468], 6104 [469]
    Urban Challenge materials are available in Canvas
  Identify and describe the processes, organizations, tools, and milestones necessary to be successful
The following outline roughly follows the INCOSE SE Handbook in terms of topics
Complete, annotated outline is posted in Canvas as “Midterm SEMP” at week 8
Homework each week requires you to complete the applicable sections

## Slide 17: DARPA Urban Challenge SEMP
Related Links
  https://www.darpa.mil/about-us/timeline/darpa-urban-challenge http://en.wikipedia.org/wiki/DARPA_Grand_Challenge
Scope
  Develop and submit for testing and competition an autonomous road vehicle able to navigate and complete a defined course in a cluttered urban environment
  Requirements (posted in Canvas Files, Assignments)
    Evaluation criteria
    California Driver Handbook http://www.dmv.ca.gov/pubs/pubs.htm
    Note also “E-stop” Guidelines
The SEMP defines the technical management plan for achieving the program objectives of a competing team

## Slide 18: DARPA Urban Challenge
Life cycle and Key Milestones: see “Urban Challenge Event Guidelines”
  Development
    Site visits (DARPA required)
    National Qualifying Event (DARPA required)
      Treat as formal “Verification”
  Final Event (DARPA required)
    Treat as “Validation”
  Extension options (business decision)
    Treat as Operations and Maintenance
  Disposal (required in all cases)
Life cycle creates the need for specific tasks and processes

## Slide 19: Alternates to DARPA Urban Challenge
    You may develop a SEMP for another project used in other courses (5101, 6102, 6104)
But - You must submit all project-specific compliance documents with HW2 , including any equivalent:
  Acquirer specifications
  Statement of work
  Integrated management plan or schedule
You should assume that I will be relatively ignorant of any alternate project, and you will have to educate me – extensively!

## Slide 20: Plan vs. Report
Plan the work that you already know must be done (Future tense)
  Processes will be contemporaneous with development (Present tense)
Apply lessons learned from similar
Report on the Work
SysEng 5101 [368] and others
Work the Plan
SysEng 5101 [368] and others
Plan the Work
SysEng 6105 [412]
SysEng 6196
Retrospective: Apply Lessons Learned
You are here↓
Don’t “report” (past tense) in SEMP

## Slide 21: DAU/DAG 4.1.2 Systems Engineering Plan
“The purpose of the Systems Engineering Plan (SEP) is to help Program Managers develop, communicate, and manage the overall systems engineering (SE) approach that guides all technical activities of the program. The SEP documents key technical risks, processes, resources, metrics, SE products, and completed and scheduled SE activities…(from customer’s perspective)
“The SEP describes the integration of SE activities with other program management and control efforts, including the Integrated Master Plan (IMP), Work Breakdown Structure (WBS), Integrated Master Schedule (IMS), Risk Management Plan (RMP), Technical Performance Measures (TPMs), and other documentation fundamental to successful program execution. The SEP also describes the program’s technical requirements, engineering resources and management, and technical activities and products as well as the planning, timing, conduct, and success criteria of event-driven SE technical reviews throughout the acquisition life cycle….
As the program’s blueprint for the conduct, management, and control of all technical activities, the SEP captures decisions made during the technical planning process and communicates objectives and guidance to program personnel and other stakeholders. The SEP should define the “who, what, when, why, and how” of the SE approach, for example:
  The program organization with roles and responsibilities, authority, accountability, and staffing resources. This includes the coordination of the program’s integrated product teams (IPTs) and their products, resources, staffing, management metrics, and integration mechanisms….
https://www.dau.mil/community-hub#All||title_asc

## Slide 22: SEMP Outline – 1
Week 1
Week 2
Notes: These two pages are the key to the first half of the semester.

## Slide 23: SEMP Outline – 2
Week 4, 5, 6
Week 3
Week 7
5. Technical Management Processes
5.1. Project Technical Plan
5.1.1. Major Events: Integrated Master Plan
5.1.2. Work Packages
5.2. Technical Management and Assessment
5.2.1. Technical Performance Management
5.2.2. Continuous Assessment
5.2.3. Other Technical Measurements
5.3. Integration with Cost and Schedule Management
5.4. Decision-Making
5.5. Issue Identification and Resolution
5.6. Risk and Opportunity Management
5.7. Configuration Management
5.7.1. Baseline Definition and Management
5.7.1.1. Configuration Identification
5.7.1.2. Configuration Status Accounting
5.7.2. Change Management
5.7.3. Requirements Management
5.7.4. Interface Management
5.8. Information Management
4. Technical Processes
4.1. Business/Mission Analysis
4.2. Stakeholder Needs and Requirements Definition
4.3. Requirements Definition, Validation, Traceability
4.4. Architecture Definition and Traceability
4.5. Design Definition and Traceability
4.6. System Analysis
4.7. Implementation
4.8. Integration
4.9. Verification and Traceability
4.10. Transition
4.11. Validation
4.12. Operations
4.13. Maintenance
4.14. Disposal
6. Organizational Investment
6.1. Environment Management
6.1.1. Program Policies and Procedures
6.1.2. Program Measurement and Assessment
6.1.3. Continuous Improvement
6.2. Investment Management
6.2.1. Product Line Investment
6.2.2. Supply
6.2.3. Acquisition
6.3. Resource Management
6.3.1. Personnel
6.3.2. Infrastructure
6.4. Quality Management

## Slide 24: SEMP Tailoring
The challenge of standards is a “one size fits all” mentality for the most generalized case
Most standards provide for customizing (“tailoring”) for the specific application
Users must decide what to keep, modify, delete
See ISEH section 8*
*All ISEH references are to ver. 4

## Slide 25: SEMP Tailoring
Standardized templates enable more consistent products and are expected for mature organizations
  The negative side is that complex programs can seldom tolerate “one size fits all” planning and execution
Tailoring
  “Tailoring is the process by which specific requirements of a standard, specification or similar document are selected and used to meet the needs of a project.”
  “Tailoring should only be undertaken when it is necessary to make or adapt an existing standard to fit user requirements, taking account of time, cost and performance.” http://web.archive.org/web/20070609192145/http://www.dstan.mod.uk/tailor_stan.pdf
“Tailoring” is a method of customizing that
  Acknowledges the standard
  Addresses the intent of the standard
  Adapts the standard to the specifics of a program to improve the technical and business performance of the program

## Slide 26: SEMP Tailoring
For this course
  Use the outline as provided
    For any section that you believe is unnecessary for your project, write your rationale for exclusion in the applicable section instead of what the plan content would be
    Feedback will be provided
  Cogency and quality are preferred over length
  Rationale must be consistent with your project description in section 1
On a real program, deviations from established templates would be managed by policy (“reserved”, “not applicable”, or simply, not there)
  Some value to preserving standard numbering

## Slide 27: Technical Planning Overview - 1
What – Project Goals; Deliverables – Must establish a common vision
When – Development Phasing, Milestones
Who – Organization
How – Processes, tools,
Where – Facilities, Location(s)
NOTE: a “Plan” is not a compliance document (e.g., SOW/Rqmt). Do not use “shall”
SEMP
1. Introduction
1.1 Document Purpose
  Why is this document being written? How is it intended to be used?
1.2 Document Scope
  What does it cover? What general subjects are not included?
1.3 Document Update
  Method and Frequency – How, and how often? Why then?

## Slide 28: Example 1.1
1.1 Document Purpose
  Why is this document being written? How is it intended to be used?
Example Problems
  How will the intent be measured or enforced?
  Process execution
  A Reference by new/ existing managers and engineers
  Are processes clear enough?
“The Systems Engineering Management Plan (SEMP) identifies and documents the approved technical management processes to be used throughout the life of the program. It is meant to be used as a guideline and reference, for new and existing managers and engineers to ensure they execute these processes consistently as documented”

## Slide 29: Example 1.2
1.2 Document Scope
  What does it cover? What general subjects are not included?
Example Problems
  Technical processes listed – what about the others?
  What processes are handled elsewhere, and how might someone find them?
  Identify single source of any specific program information
“This SEMP guides personnel as they execute Systems Engineering and Integration functions such as: requirements analysis, requirements validation, functional analysis, functional verification, synthesis, verification/ validation, system analysis, and systems integration and control. Figure 1.2-1 depicts the systems engineering (SE) process”

## Slide 30: Example 1.3
1.3 Document Update
  Method and Frequency – How, and how often?
Example Problems
  Event-based or calendar based updates?
  Periodic or on-condition?
  Assess need for change before committing to change (potential program cost savings)
  Does the nature of what is being managed change character at life cycle stage transitions?
“The Systems Engineering Management Plan (SEMP) will be reviewed and updated in conjunction with each technical review identified in the Integrated Master Plan (IMP). Necessary changes will be made and reviewed at the technical review to ensure that the plan is always consistent with program needs. Organizations involved in SEMP updates are identified in section 3”
Notes: Ahead of each technical review might be too often, and it’s the busiest time – getting ready for a review; why not soon after the review?

## Slide 31: Technical Planning Overview - 2
What – Project Goals, Deliverables
When – Development Phasing, Milestones
Who – Organization (section 3)
How – Approach, processes, tools
Where – Facilities, Location (as needed; can be addressed in “organization” and verification/validation)
1.4 Program Summary
1.4.1 Program Objectives and Scope
  What are the primary objectives (programmatic and technical)? How will you determine “success”? Are there any limitations or key assumptions? Information in this section will be used to evaluate adequacy of this plan
1.4.2 Project Summary and Deliverables
  Describe major stages of the project, key milestones and deliverables in each stage. These can be more than hardware and software
1.4.3 Technical Description
  Describe the system and the strategy or approach to achieving the technical objectives

## Slide 32: Example 1.4.1
1.4.1 Program Objectives and Scope
  What are the primary objectives (programmatic and technical)? How will you determine “success”? Are there any limitations or key assumptions? Information in this section will be used to evaluate adequacy of this plan
Issues and Discussion
  This discussion is critical for everything that follows – don’t treat it as mere “boilerplate”
  Keep the end in mind (Covey)
“The purpose of this program is to develop, verify, and deliver ABC product for evaluation [or deployment] to the XYZ Corporation, the acquirer
  The success of these product deliverables depends on improving the technical maturity of the obershammer technology from the current TRL 5 to TRL 8.
  Key measures of technical success include improvement in the five program KPPs as follows: …
  Key measures of programmatic success include delivering prototypes per the Integrated Master Schedule on xx December 20yy, …
  Program constraints include…
  Programmatic risks being managed include…

## Slide 33: Example 1.4.2
1.4.2 Project Summary and Deliverables
  Describe major phases of the project, key milestones and deliverables in each phase. These can be more than hardware and software
Issues and Discussion
  This section sets up the rationale for the plan – why and how certain things are done to meet intermediate and final deliverables
“This program is divided into three major development stages: (1) technology demonstration, (2) engineering development, and (3) integration and demonstration. Within each stage are a number of milestones…
Key deliverables for these respective stages are”…

## Slide 34: Example 1.4.3
1.4.3 Technical Description
  Describe the system and the strategy or approach to achieving the technical objectives
  Describe how requirements for all life-cycle phases will be developed and incorporated
Issues and Discussion
  The technical plan must reflect the strategy
  The approach must plausibly lead to satisfying the objectives. Various development models are possible (next slides)
“The ABC system is ...
“To achieve the technical objectives the program will use a spiral development model as indicated in figure 1.4.3-1. This approach is appropriate because the end state requirements are uncertain. In each spiral there will be a phase for requirements identification and development, prototyping, verification and validation. Simulation will be used to ensure that the overall program is making progress …”

## Slide 35: System Concepts Review
Now moving to the ‘Mission Concept Review’
If you already had this proposed new system
  How would you be using it?
  What would it do for you?
  Would it replace anything that exists now?
  Who would use it?
  How would that be better?
  What would improve about mission performance?
  Would maintenance, or initial costs be better?
  What could go wrong?
  Could it be turned against us?
  Etc.

## Slide 36: “Systems Engineering” Definitions
ISO 15288 – 2015, “Systems and Software Engineering – System Life Cycle Process”, http://www.15288.com/
“4.31 System…
  “Combination of interacting elements organized to achieve one or more stated purposes
    “NOTE 1 – A system may be considered as a product or as the services it provides”
No explicit definition of “systems engineering” in the standard

## Slide 37: System vs. Environment
A key job is to discern (or define) the scope and boundary of the system: What’s in? What’s out?
System
Environment or “context”
System Boundary
Inputs &
Influences
Outputs

## Slide 38: Elements of a “System”
Product
Support
Training
Data
Facilities
Much more than the “product”
From Blanchard, “System Engineering Management”, 3rd Edition

## Slide 39: Systems, Subsystems, Components
Common usage organizes a hierarchy of system components
System
  Segment
    Subsystem
      Component
        Parts
One’s “system” is someone else’s “component” or “subsystem” – no absolutely correct label
A “system” is based on your scope of responsibility
Top-down

## Slide 40: Design Influence Over Time
Transition from conceptual design (strong SE influence) to detailed design (weaker SE influence)
SE Management emphasis changes
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, 4th Edition

## Slide 41: System Life-Cycle Engineering
Acquisition
  Development, Verification, Production (Implementation), Deployment (Transition)
Utilization (also called, “sustainment”)
  Operations, Maintenance (and Training), Disposal
The essence of Concurrent Engineering (Blanchard 2.2.1)
Need to address all life-cycle stages during early design
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, 4th Edition

## Slide 42: Concurrent Engineering
“A systematic approach to the integrated, concurrent design of products and their related processes, including manufacture and support. This approach is intended to cause the developers, from the outset, to consider all elements of the product life cycle from conception through disposal, including quality, cost, schedule, and user requirements”
A Concurrent Engineering strategy needs to be reflected in the plan: organization, processes, review milestones
“Concurrent Engineering” does NOT mean, “everybody start engineering now”
From Blanchard, “System Engineering Management”, 4th Edition, 34, note 24, Winner et al.

## Slide 43: Minimizing Lifecycle Cost (LCC)
Development costs
  Design once (minimize iteration)
From Blanchard, “System Engineering Management”, 3rd Edition
Design and Development
Production and/or construction
Identified Need
Operational use and
Maintenance support
Retirement and
material disposal
Design for operations and support
  Biggest % of life-cycle costs (LCC)

## Slide 44: Development Models – Acquisition Environment
Traditional process development models
  Linear with limited feedback
    Waterfall model
    V model today, Digital Twin
Evolutionary acquisition strategies integrate advanced, mature technologies into producible systems that can be deployed to the user as quickly as possible.
  An evolutionary acquisition strategy matches available technology and resources to approved, time-phased, capability needs.
Development and lifecycle models that support systems engineering with an evolutionary acquisition strategy
  Incremental (phased waterfalls) (PrePlanned Product Improvement)
  Spiral model deleted in latest US Department of Defense Acquisition Policy (DOD Instruction 5000.02, December 2008)

## Slide 45: System Development Models - 1
Waterfall – finish each activity before proceeding to next
“Ideal” approach; supported by TOC (don’t start next activity until completing the prior activity)
Seldom enough time allocated
“Need” often outpaces schedule
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, 4th Edition

## Slide 46: System Development Models - 2
‘Vee’ – Organizes Waterfall model into two comple-mentary parts
Associates verification with associated requirements at each level of hierarchy
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, 4th Edition

## Slide 47: System Development Models - 3
Spiral – incorporates prototyping to reduce development risk (define, build, test, refine, test, refine….)
No longer in US DODI 5000.02 Acquisition Policy (but deeply embedded in people’s consciousness)
From Blanchard, “System Engineering Management”, 4th Edition

## Slide 48: System Development Models - 4
Agile Development*
  Emphasizes continuous validation
  Combines “incremental” with “spiral” when desired end state is unknown but individual increments can be defined
  “Finish-to-finish” requirements, design, and integrate
Requirements
Design
Integrate
Verify
Build
Validate
Time
Carson, Ronald S., “Can Systems Engineering be Agile? Development Lifecycles for Systems, Hardware, and Software”, Proceedings of INCOSE 2013.
See also Dove et al., Proceedings of INCOSE 2015
after Carson 2013

## Slide 49: System Design Considerations
Drawn from all stages of system life-cycle
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, 4th Edition

## Slide 50: Development Phasing
Development usually progresses through distinct levels or stages:
  Concept level, which produces a system concept description
  System level, which produces a system description in terms of system characteristics and constraints
  Subsystem/component level, which produces first set of subsystem and component product performance descriptions, then a set of corresponding detailed descriptions of the products’ characteristics essential for the production
From DAU SE Fundamentals

## Slide 51: 2.0 Reference Documents – 1
2.0 Identify references on which you are depending and which are cited in the text. How are these references tailored, prioritized, and applied?
2.1 Industry References
Standards, industry handbooks, other references. Identify which are “guidance” (provide useful information) and which are “compliance” (must be adhered to). For “Compliance”, the referencing section of the plan must address how compliance will be shown. List in a tabular form
Document Number | Document Title, Version, Date | “Guidance” or “Compliance”?
ISO/IEC15288 | Systems and Software Engineering – System Life-Cycle Processes, 2nd Edition, 2008-02-01. | Guidance

## Slide 52: 2.0 Reference Documents – 2
2.2 Acquirer References (tabular format)
Acquirer-specific references. Might not be applicable for supplier-funded development
2.3 Enterprise References (tabular format)
Your company items that apply to more than just your program – You need to hypothesize a larger organizational context for this project
2.4 Program References (tabular format)
Project-specific references controlled by the performing organization. May include, for example, program management plans or plans subordinate to the SEMP (e.g., risk management, requirements management, etc.)

## Slide 53: Questions for Tonight?
HW1 – do it if not done
Next week:
  Week 2 Readings in Syllabus - be prepared to discuss in class
    ISEH 3, 6.1, 6.2, 9.7, 10.1-10.13
  HW2 – Due
  Canvas Discussion Board
    Is ONLY to be used when
      Class is not held (e.g., Snow day), or
      You have arranged in advance to miss class
    If used, posts are due at beginning of class time for credit
  Lecture 2: Program Organization
End – Good night!

## Slide 54: Program Completed
Missouri University of Science and Technology
© 2006-2020 Curators of University of Missouri