## Slide 1: SysEng6196 Systems Engineering Capstone
Dr. Lou Pape
2 – Program Organization

## Slide 2: Organizing for the Work
The project organization is a system
The organization system must be designed to accomplish the work identified (see SEMP section 1)

## Slide 3: Allocating the Work
The Work Breakdown Structure (WBS) organizes & allocates the work
The Organizational Breakdown Structure (OBS) provides the design solution for allocating the work to organizational elements
The allocation is the Responsibility Assignment Matrix (RAM)
This is SE applied to organizations
Responsibility Assignment Matrix

## Slide 4: SOW, WBS, Organization
What to do: SOW with Deliverables
§1
Who will do it: Organization
How to organize the work: WBS
How to do the work:
SEMP §4 & §5
Detailed task
Definition
Detailed task
Allocation
Responsibility Assignment Matrix
§3

## Slide 5: 3.0 Program Organization
3.1 Work Allocation: WBS
  Provide a summary work breakdown structure that accomplishes the work identified in section 1, and define tasks to the tier 3 level.
Organization (≠ WBS)
RRAA
Organizational Integration

## Slide 6: WBS and Organization
Why describe WBS as part of “Organization” in SEMP?
  Program deliverables need to be clearly defined and organized to ensure they are accomplished
  Defining top levels of WBS is necessary to establish roles and responsibilities for organizational elements
WBS is not an organizational chart (WBS ≠ Organization) – but a Task and Deliverable organization
Detailed WBS defines organization of work packages prepared for the purposes of program planning, budgeting, contracting and reporting (more under §5.1, Technical Planning)
Responsibility assignment matrix (RAM) allocates WBS elements to organizational elements
Notes: Deliverables: plans, hardware, software, reports, manuals, training, status, reviews,

## Slide 7: Work Breakdown Structure (WBS)
The WBS is a product- or task-oriented tree that leads to the identification of the activities, tasks, subtasks, and work packages that must be performed for the completion of a given program
  Product-oriented: deliverable is product per specification or drawing
  Task-oriented: deliverables are typically reports (information)

## Slide 8: WBS
WBS must include at least three levels of activity:
  Level 1: Identifies the total program scope of work, and the system to be developed and delivered to the acquirer
  Level 2: Identifies the various sub-projects and activities that must be completed in response to program requirements
  Level 3 and lower: Identifies the activities and tasks that are directly subordinate to the next-higher-level items
Task decomposition is similar to functional decomposition

## Slide 9: Example WBS to Level 3
Appropriate for SEMP §3 – but needs task completion criteria in the text
More detail is required in SEMP §5.1
Level 3

## Slide 10: WBS Development
Key elements of WBS
  Describe all work necessary to deliver contractual obligations (focus of 3.1)
  Describe how work packages will be defined for cost/schedule control purposes (focus of 5.1, but introduced here)
  Clearly describe work products (outputs)
  Clearly describe inputs to tasks
  Eliminate duplicate work effort (supported by clarity of task descriptions, inputs, and deliverables)

## Slide 11: SEMP §3
3.1 Work Allocation: WBS
  Provide a summary work breakdown structure that accomplishes the work identified in section 1, and define example tasks to the tier 3 level
3.2 Organization Structure (OBS) and Responsibility Assignment Matrix (RAM)
3.3 RRAA (Role, Responsibility, Authority, Accountability)
3.4 Organizational Integration
Notes: Role Responsibility Authority Accountability

## Slide 12: Organization
Organizational Breakdown Structure (OBS) needs to support achieving program objectives
  Similar to product architecture (functional decomposition)
Organizational structures are tailored to most effectively accomplish the required functions
  The goal is to achieve the most effective utilization of resources to accomplish the program objectives
  There are things outside the program that influence it
Apply Systems Engineering – to define, build, control, and maintain the organization
  We usually think in terms of the product, but this is for your people and your organization structure

## Slide 13: Organization for SE
Many different ways to organize projects, programs, people
No “perfect” organization structure
Always need to identify and integrate across interfaces
  Functional
  Project
  Technical specialty
Need clear alignment of authority and responsibility
Organization structure and allocated budget are big influencers on program SE success
  Discussion question: Why? (this is where YOU talk)

## Slide 14: Anarchy vs. Organization
Must we have “organization”?
“If all are responsible, then no one is responsible”
    Example: Public parks
Some structure is necessary to ensure results
  Trend toward “flattened” hierarchies to reduce layers/levels of management (recently)
  Requires
    High-coordination by a few people, or
    High-responsibility by all people (“see a need and satisfy it” culture)
Notes: Flattened organization is “Lean”

## Slide 15: 3.2 Organization Overview
Provide a graphical organization chart
Provide a summary description of how the relationships among organizational members help achieve Program Mission and Objectives [see §1]
Explain any differences compared with the WBS and how the program will ensure all work can be efficiently accomplished
Include a responsibility assignment matrix (RAM) that links the organizational structure to the WBS using ‘RACI’
Notes: Responsible, Accountable, Coordinate, Inform

## Slide 16: Review of Alternative Organizational Structures
Alternatives
  Functional
  Project
  Matrix
  Integrated Product Teams
How to select? Do a Trade Study!
  Criteria include
    All work allocated to capable organizations (feasibility of organization)
    Manage risks of partitioning organization and work
    Enterprise organization support, and resource contention – how do you handle that?

## Slide 17: Functional Organization Structure
Sometimes referred to as the “classical” or “traditional” approach
Involves the grouping of specialties or disciplines into separately identifiable entities
The depth of the individual elements of the organization will vary with the type of project and level of emphasis required
Is well suited for a single project operation
May not be as appropriate for large multi-product firms or agencies

## Slide 18: Functional – In Parallel with a “Project” Organization
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, Fourth Edition
Projects “borrow” expertise from “central” engineering (or mfg, finance, etc.)
Retain capability in central org
Less project control of resources

## Slide 19: Functional Organization Structure -Pros and Cons
Advantages:
  Enables the development of a better technical capability for the organization
  The organization can respond more quickly to a specific requirement
  Budgeting and cost control are easier
  The channels of communication are well established
Disadvantages:
  Difficult to maintain an identity with a specific project
  Concepts and techniques tend to be functionally oriented with little regard for project requirements
  Reduced acquirer/customer orientation

## Slide 20: Project Organization
Employees assigned to projects
Enhanced project control
Diminished central organiz-ational capability
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, Fourth Edition

## Slide 21: Product-Line/Project Organization Structure –Pros and Cons
Advantages
  The lines of authority and responsibility for a given project are clearly defined
  Strong acquirer (customer) orientation
  High degree of personnel loyalty, motivation, and morale
  Personnel expertise can be assigned and retained exclusively on the project
  Greater visibility relative to all project activities
Disadvantages
  The application of new technologies tends to suffer without strong functional groups and the opportunities for technical interchange between projects
  A duplication of effort, personnel, and the use of facilities and equipment
  Difficult to effectively utilize personnel in the transfer from one project to another
  The continuity of an individual’s career, growth potential, and opportunities for promotion are often not as good when he or she is assigned to a project for an extended period of time

## Slide 22: Matrix
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, Fourth Edition
Employees retained in central organization
Projects assign tasks to an organizational element, not a person

## Slide 23: Matrix Organization Structure
An attempt to combine the advantages of the pure functional organization and the pure project organization
Enables staffing the project with project - specific personnel
Functional departments are responsible for maintaining technical excellence and exchange of technical information between projects
May form a two- or multi- dimensional structure
  Projects representing potential profit centers
  Functional departments identified as cost centers

## Slide 24: Matrix Organization Structure Pros & Cons
Advantages
  1. The project manager can provide the necessary strong controls for the project while having ready access to the resources from many different function-oriented departments
  2. The functional organizations exist primarily as support for the projects
  3. Technical expertise can be exchanged between projects with a minimum of conflict
  4. Authority and responsibility for project task accomplishment are shared.
  5. Key personnel can be shared and assigned to work on a variety of problems
Disadvantages
  1. Each project organization operates independently. Duplication of efforts is possible/likely
  2. May be more costly in terms of administrative requirements
  3. The balance of power between the project and the functional organizations must be clearly defined initially and closely monitored thereafter
  4. From the perspective of the individual worker, there is often a split in the chain of command for reporting purposes

## Slide 25
Goal: align organization to product structure to ensure an integrated product
  Product element integration (architecture)
  Life-cycle integration
Identifying, defining and managing interfaces is very critical in Integrated Systems Development
The objective is to create a team of qualified individuals that can effectively work together to solve a problem in response to a given requirement
They are established to concentrate on those activities that significantly impact selected performance factors, cost of ownership, and configuration management
Integrated Product Teams (IPTs)

## Slide 26: Integrated Product and Process Development (IPPD)
The Department of Defense defines IPPD as a “Management technique that simultaneously integrates all program activities throughout the life cycle, include systems management, development, manufacturing, testing, deployment, operations, support, training, and eventual disposal. Using IPPD, multi-disciplined Integrated Product/Process Teams (IPTs) shall simultaneously optimize the product, product manufacturing, and supportability to meet system cost and performance objectives” [emphasis added]
From Blanchard, “System Engineering Management”, 4th Edition , 370, note 4, DODR5002.R

## Slide 27: Key Characteristics
IPTs are established to produce a specific product or service – all team members/functions work together toward the common goal
It is multidisciplinary – includes various disciplines and domains
Members usually have mutual, as well as individual, accountability
Integrated, concurrent decision making – empowered to make decisions within specific product or service goal (but within the interfaces)
Needed: Planned integration among teams towards system goal (a challenge!)

## Slide 28: Functional Organization with IPTs
Life-cycle focus
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, Fourth Edition

## Slide 29: IPT Charter
IPTs are established by designated high-level authority in the organization
The representative team members must
  Be well qualified in their respective areas of expertise
  Empowered to make on-the-spot decisions
  Proactive relative to team participation
  Success-oriented
  Resolved to addressing the problem assigned

## Slide 30: IPT Planning
In addition to organizing itself, the PDT/IPT needs to have a thorough knowledge of the task at hand
They need to understand the project objectives, the specifications/acquirer requirements, design targets, cost, and schedule
This information needs to be given to the team(s) by the program manager or management team
The requirements should be thoroughly reviewed
A team charter and execution plan need to be established with clear responsibility, accountability, and authority
Notes: Product Development Team/Integrated Product Team

## Slide 31: IPTs and Functions – Example 1
Mix of “products” and traditional “functions” at top level
Unambiguous elemental product responsibility
Ambiguous system product responsibility
Can lead to
  Diffusion of system product responsibility and authority
  Challenges to integrate system elements

## Slide 32: IPTs and Functions – Example 2
Combined IPT/Function organization
Improved product integration

## Slide 33: System Engineering Organization
What’s the role of SE management in IPPD?
  Help design the organization to achieve program objectives during program planning
  Help define:
    Schedule (tasks and deliverables)
    Budget (budget for tasks)
    Technical performance and compliance
  Help ensure organizational integration during execution
    Integrated Master Schedule (IMS) integration
    Facilitate Product/deliverable handoffs

## Slide 34: Alternate SE Deployment
SE isolated from product development
  Role limited
SE integrated into product development
  Either retain SEs at top level or deploy to each subordinate team

## Slide 35: Responsibility Assignment Matrix (RAM)
Connects SEMP§3.2 Organization to§3.1 WBS
Introduces §3.3 – RRAA
http://www.mindtools.com/pages/article/newPPM_RAM.htm
Define the deliverables (WBS)
Identify the people (organizational breakdown structure – OBS)
Map Deliverables to people/organization as (RACI)
  R = Responsible (People who do the work)
    [If multiple organizations are Responsible, designate exactly one as R*: People who do the work AND are responsible to ensure that it gets done]
  A = Accountable (People legally responsible that the work gets done correctly)
  C = Consulted (People who provide input before and during the work – who coordinate on the work)
  I = Informed (People who are kept informed of progress)
Copyright © Mind Tools Ltd, 1995-2010, All Rights Reserved. Reproduced with permission
Notes: Role, Responsibility, Authority, Accountability

## Slide 36: Example RAM
http://www.mindtools.com/pages/article/newPPM_RAM.htm
Copyright © Mind Tools Ltd, 1995-2010, All Rights Reserved. Reproduced with permission.
WBS 
Org. 
Be careful of >1 “R” in any column; it may lead to conflicts or gaps

## Slide 37: Systems Engineering a RAM
 | WBS | WBS | WBS | WBS | WBS
Org |  |  |  |  | 
Org |  |  |  |  | 
Org |  |  |  |  | 
Org |  |  |  |  | 
Organization (OBS)
Work (WBS)
Allocating work from WBS to elements of organization is a standard SE task:
  Allocate requirements (work from WBS) to…
  Elements of the organization architecture (the OBS)

## Slide 38: Roles, Responsibility, Accountability and Authority
3.1 WBS
3.2 Organization and Responsibility Assignment Matrix
3.3 RRAA
3.4 Organizational Integration

## Slide 39: SEMP Section 3.3
3.3 Role, Responsibility, Authority, Accountability
  Describe each role (summary of what they do), specific responsibilities, specific authority, to whom they are accountable, and responsibilities for specific program results or deliverables. This collection of information can be described as a “charter”. These descriptions should be consistent with the allocation of tasks in the following sections and the WBS

## Slide 40: Responsibilities and Authority
Responsibilities must be clear: what is the expectation (organizational requirement)?
  WBS elements are allocated to elements of the organization
  Deliverables need to be clear
  Bad role/responsibility definition and unclear team interfaces will result in duplication of effort, conflict, or gaps
Authority and Accountability
  Team leaders and managers must verify that teams are exercising their authority appropriately and that they are accountable for their assigned responsibilities
  Authority must align with responsibility
    Delegate authority to execute the responsibility
      Budget; people; other resources (see notes below)
Notes: Other resources: tools, factory space, test equipment, storage, office space, computer time…

## Slide 41: Roles
3.3.1. Program Leadership
  Program Management, acquirer engagement, cost and schedule, etc.
3.3.2. Technical Leadership
  Chief Engineer or Chief Architect, Chief Systems Engineer, other function or product team leaders
3.3.3. Teams and Functions
  Integrated product and process development (IPPD) and/or function-based organization
3.3.4. Key Suppliers and Supplier Integration (who buys stuff for you)
  “Acquisition” per the Handbook. Identify suppliers who are critical for program success and how they are integrated into the program SE execution
3.3.5. Associate organizations
  If applicable, identify partners or other suppliers who deliver to a common acquirer on a specific project
3.3.6. Acquirer (your customer)
  Describe any execution-level involvement of acquirer organizations, such as working groups, integrated product or process teams
3.3.7. User
  If different from acquirer identify their specific involvement in working groups, integrated product or process teams, evaluation (validation), etc.

## Slide 42: Acquirer, Supplier, and Other Supplier Relationships
The system engineering function may appear at several levels, evolving from the acquirer and down to the supplier and lower-tier suppliers
System engineering tasks are implemented across multiple organizations
  The acquirer may establish a system engineering organization
  These tasks may be allocated to the supplier
The responsibility along with the authority must be clearly defined from the beginning
Formal and informal channels of communication must exist between various entities involved

## Slide 43: Supplier Organization and Functions
“Supplier” is anyone that provides materials, products, and/or services to an acquirer
System engineering requirements must be traceable from the acquirer to all “key” suppliers (any doing SE)
Suppliers
  Design or Manufacturing/Production development
    Need product definition for design or build
  Standard or “Commercial off-the-shelf” (COTS) components
    “You get what they’ve got”
    “Modified off the shelf” is an oxymoron (see “development”)
  Products vs. services
  Tiered suppliers

## Slide 44: Acquirer Organization and Functions
The acquirer and user organizations may be different
  The user vs. your acquirer
  The requirements associated with the latter should support the objectives specified for the former
  Why might this not work in practice?
The acquirer must clarify system objectives and program functions and provide managerial backing when delegating responsibilities
The system engineering functions can be accomplished within either the acquirer’s or the supplier’s organizational structure, or the combination
Acquirer ($)
Users
Supplier
Dynamic Tension

## Slide 45: Organization RRAA
Clearly identify
  Role – Why are they included in the discussion? What over-arching function or purpose do they serve?
  Responsibility – Identify major deliverables. What would be missing from program success if they were omitted?
  Authority – Summarize the authority given to the organization role. Often this is in the form of control of resources (money, people, facilities, schedule). What decisions can be made autonomously?
  Accountability – To whom are they responsible? Who will be affected if there are problems (late, over budget, inadequate performance, etc.)? What are the key measures of success for the organization?
Be consistent with Responsibility Assignment Matrix (RAM)

## Slide 46: 3.4 Organizational Integration
3.1 WBS
3.2 Organization and Responsibility Assignment Matrix
3.3 RRAA
3.4 Organizational Integration

## Slide 47: Organizational Integration
Organizational integration is necessary because of partitioning
  Similar to product or system integration
Ensures that
  Diffuse responsibilities are coordinated
  Effort is performed consistently
    Suppliers
    Acquirer
    Technical approach

## Slide 48: 3.4.1 Working Groups and Boards
Working groups and boards may have different scope
  Integrate across inter-organizational boundaries
    Example: Interface Control Working Group – includes acquirer, suppliers, and project
  Integrate across intra-organizational boundaries
    Example: Configuration Control Board – IPTs, various engineering or non-engineering functions
Consider
  Boundaries between organizations that create the need for focused integration based on risk
Do NOT create boards and working groups to
  Diffuse responsibility and decision-making – leads to the “paralysis of analysis” and lack of leadership
  Duplicate responsibilities of existing organizations
DO
  Identify clear charter, scope: what unique service or function is provided by board or working group that cannot be provided by any single organization? Describe the RRAA

## Slide 49: 3.4.2 Technical Specialty Integration
Identification of expertise
  Software
  Human Factors
  Safety
  Security
  Manufacturing
  Disposability
  Quality
  Environment
  Reliability
  Maintainability
  Logistics/ Supportability
  Affordability
  Interoperability
  Electromagnetics
  Mass properties
Program Tasks
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, Fourth Edition

## Slide 50: Why “Specialties”?
Sophisticated technology demands narrow specialization to apply the state-of-the art
Large, complex systems benefit from overarching and consistent design approach to handling specialized disciplines
How can the project best deploy specialty engineers to their product development/mfg/etc.?

## Slide 51: Common Tasks for Specialties
Describe common approaches across all specialties
Identify any unique efforts for each applicable specialty area
  Consider program planning
  Application of specialty areas’ standards
  Requirements development
  Design guidance and design analysis
  Developmental testing
  Verification (both test and analysis)
  Required operations, maintenance, or disposal support
This section is about the strategic approach to deploying specialties, not a process description section
The intent is not to duplicate information in sections 3.3 or 4, but to identify the roles of specialists being identified
This is especially important in a product-based organization structure

## Slide 52: Software
Software is not usually classified as a “specialty” but as another engineering discipline (e.g., electrical, mechanical…)
Treatment is needed at the system level because of the strong influence of software architecture on system design and performance
This can create tension in the management of the system development

## Slide 53: SW Engineering
Parallels Systems Engineering Life-Cycle
  Planning
  Requirements
  Architecture
  Design
  Code (Element Fabrication)
  Assembly, Test & Fix (Verification & Correction)
  Production
  Maintenance
    Correction
    Improvement
Some degree of concurrence and iteration
From Blanchard, “System Engineering Management”, 4th Edition

## Slide 54: Reliability
Reliability is the probability that a system or component will perform its required functions under stated conditions for a specified period of time
Elements of
  Probability
  Duration
  Conditions
    Input/environments
    Output/performance

## Slide 55: Failure Rate Over Time
“Infant morality”
Constant l
  Random failure
    Electronic parts
Wear-out
   increasing
  Mechanical parts
From Blanchard, “System Engineering Management”, 4th Edition

## Slide 56: Reliability Summary
Strongest influences on reliability are temperature and temperature fluctuations
  Large thermal design margins give higher reliability systems
Life-cycle activity
  Analysis: very little “reliability testing” to failure of modern avionics with MTBFs > 1,000 hours
  Overstress testing applied to components and subsystems during development to ensure design margin, instead
  Environmental stress testing applied on manufacture to find weaknesses
  System integration level DT&E & IOT&E is a late (but far too frequent) time to find reliability weaknesses
  O&S data gathering for design improvements

## Slide 57: Maintenance Restores Functionality after failure
3 levels of maintenance –
  “Org” (organ-ization), “Intermediate”, “Depot”
  Analogous to “Home”, “Shop”, “Manufacturer”
Failures are not always con-firmed after removal (“no fault found”)
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, Fourth Edition
Notes: Original Equipment Manufacturer - OEM

## Slide 58: Maintenance Cycle Times
M
LDT
ADT
Unit dependent
System-controlled
System-dependent
Waiting for spare part, test equipment, facility, transportation
Delays for personnel – related issues (assignment, strikes, other organization issues)
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, Fourth Edition
MDT

## Slide 59: Availability
Inherent Availability A0
  Probability that system will satisfy requirements at any point in time, under stated conditions
  Ai = MTBF/(MTBF + Mct) [Mct = mean correction time]
  Characteristic only of the equipment
  Suppresses preventive maintenance, administrative and logistics delays
  Enables trades between MTBF and Mct
For some operations with no allowed maintenance, Ai = Reliability
For DARPA Urban Challenge, there’s no maintenance during the Final Event, so Ai = Reliability

## Slide 60: Human Factors
From Blanchard, “System Engineering Management”, 4th Edition
Job/duty/tasks
Anthropometrics
  Vision
  Environment
  Reach/motion
Cognition and psychology
  Complexity
  “Non-machine” behaviors
Non-Mil; ADA accommodations
Notes: Americans with Disability Act

## Slide 61: Safety and Hazard Analysis
Goal: ensure safety of personnel involved with system
  Operators, maintainers, and “casual” passers-by
Tasks
  Planning and Reviews
  Fault tree analysis (FTA)
  Hazard identification
    Causes
    Effects
    Classification
    Rate of occurrence
    Corrective/preventive measures
    Similar to (and uses) FMECA
  Risk analysis
  Data collection and analysis
  Safety Training
  Safety Test and Evaluation
Notes: Failure Modes/EffEcts Criticality Analysis

## Slide 62: Security
Design for intended operators, balanced with…
Design against unauthorized users and threats
  Physical security – access control
  Anti-tampering – passive
  Detection and annunciation
    Some similarities regarding protection against electronic/ information attacks (viruses, denial of service)
Define and protect system boundaries (points of entry)
Information Assurance / Security
  Balance Confidentiality, Integrity, Availability (CIA)
  Certified Information Systems Security Professional (CISSP) (Cf. http://en.wikipedia.org/wiki/CISSP )

## Slide 63: Producibility / Manufacturability
Considerations
  Can it be made? – Technical feasibility
  With acceptable costs? – Economic feasibility
  With what impacts? – Sustainability feasibility
    On workers
    On environment
    During manufacturing

## Slide 64: Elements of Logistics and Supportability
Plans
People
Information Infrastructure
Physical Infrastructure
Repair Infrastructure
Experience Data and Communications
Transportation and Handling
Technical Data
Spares and Consumables
People
Much more than the “system” being supported
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, Fourth Edition

## Slide 65: Quality
Old: “Inspect quality in” – Big feedback loops
Current: “Total Quality Management” and equivalents
  TQM is a total integrated management approach that addresses system/product quality during all phases of the life cycle and at each level in the overall system hierarchical structure.
Elements
  User satisfaction (not just meet requirements)
  Continuous improvement
  Minimize variation
  Enterprise activity
Much more in lecture 8 ff…
See also “CMMI”

## Slide 66: Environmental Engineering: Green Production – Closing the Cycle
Reduce waste by aligning costs and benefits
Raw Materials –
Profit to producer
Finished
Product –
Profit to producer
Operations and Support Materials – Profit to user and suppliers
Disposal, Reuse, or Recycle? Profit? Costs?
Manufacturing “waste”
Tailings
Operations “waste”

## Slide 67: Affordability & Life-Cycle Costing
Why do we care about life-cycle cost?
  Operations and support vs. acquisition
  Time value of money
  Disposal vs. manufacturing
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, Fourth Edition

## Slide 68: Hidden Future Costs
Tendency to ignore future O&S costs – Why?
Out-years are “not my problem”
Limitations on acquisition funds may force known acceptance of higher LCC
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, Fourth Edition

## Slide 69: Cost Considerations in the System Life Cycle
Future LCC fixed early in product develop-ment cycle
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, Fourth Edition

## Slide 70: Demanufacturing & Disposal
Enable “disassembly” and
  Reuse
  Recycle / remanufacturing
  Recovery of materials and components
    Example: Grinding vs. burning stumps
Disposal is a last resort
From Blanchard and Fabrycky, “Systems Engineering and Analysis”, Fourth Edition

## Slide 71: Interoperability
System element life-cycles have different time-lines
  Technology upgrades
  Support infrastructure
  Associated systems
Need to “expose” and control internal interfaces to enable “system-of-system” behavior and interoperability
From Blanchard, “System Engineering Management”, 4th Edition

## Slide 72: Electromagnetics (E3)
Electromagnetic effects are based on the combination of radiated and conducted electrical signals
Operations of most electronic devices both affect and are affected by the local electromagnetic fields
Standards affect consumer products
Systems composed of hundreds and thousands of electronic components and wiring must ensure
  EM compatibility (no self-jamming)
  Acceptable EM susceptibility – ability to operate in local environment
  Acceptable EM emissions – limits on what is produced
Affects physical placement of electronics and wiring
Some group must keep track of all of this; verify & provide guidance
Might be important for Urban Challenge, including E-stop
Notes: Electromagnetic Environment Effects

## Slide 73: Mass Properties
System level needs to account for total weight and distribution of weight
Each element will be allocated weight as part of requirements
Location of element (determined by system design) determines distribution of weight
Some group must keep track of all of this
Total weight = sum(weights)
Center-of-mass= sum(weight x distance)
sum(weight)

## Slide 74: 3.4.2.3 Integrating Specialties
Describe how the specialists are organized and deployed, their specific roles, responsibilities, authority, accountability, and how they are integrated across the organization (vertically – a single specialty throughout the whole organization, or horizontally – all the specialties at a given level)

## Slide 75: Example SEMP – GLAST / LAT
Gamma-ray Large Area Space Telescope / Large-Area Telescope
  Review / discuss TOC, 4.1, 4.2, 4.2.3, 4.2.6, 5.1 regarding “Organization”
  What is provided?
  What appears to be missing? What risks are generated?
    Note roles of ISE and other teams

## Slide 76: Questions for Tonight?
Next week
  Reading as Assigned in Syllabus – ISEH 4
  Homework 3 - SEMP Section 3
  Read Lecture 3: Technical Processes
Following week: Lecture 4 Technical Planning and Assessment
  Reading: ISEH 5.1, 5.2, 5.7
  Homework 4 - SEMP Section 4
End – Good night!

## Slide 77: Program Completed
Missouri University of Science and Technology
© 2011-2020 Curators of University of Missouri