## Sheet1
Tabular WBS
LEVEL 1 | LEVEL 2 | LEVEL 3
1. A&Bs Unmanned Autonomous Vehicle | 1.1 Maintenance | 1.1.1 Spare Parts
1.1.2 Repair Parts
1.1.3 Repair Tooling
1.1.4 Vendor Relations
| 1.2 Facilities | 1.2.1 Construction/Conversion/Expansion
1.2.2 Equipment Acquisition
1.2.3 Maintenance
1.2.4 Utilities
| 1.3 Safety | 1.3.1 Equipment/Apparel Purchases
1.3.2 State/Federally Compliant
1.3.3 EPA Compliant
1.3.4 Safety Procedures
| 1.4 Operations Site Activities | 1.4.1 System Assembly
1.4.2 System Installation
1.4.3 System Checks
1.4.4 Contractor Tech Support
1.4.5 Site Construction/Modification
1.4.6 System Transportation
| 1.5 Support Equipment | 1.5.1 Test and Measurement Equipment
1.5.2 Support/Handling Equipment
| 1.6 Quality | 1.6.1 Defect Prevention
1.6.2 Defect Management
1.6.3 Documentation
1.6.4 Customer Support
| 1.7 Training | 1.7.1 Equipment
1.7.2 Services
1.7.3 Facilities
| 1.8 Data | 1.8.1 Technical Publications
1.8.2 Engineering Data
1.8.3 Support Data
1.8.4 Management Data
1.8.5 Data Depository
| 1.9 IT | 1.9.1 Storing Data
1.9.2 Retrieving Data
1.9.3 Transmitting Data
1.9.4 Manipulating Data
| 1.10 Testing | 1.10.1 Test and Engineering Support
1.10.2 Mock Trials
1.10.3 Testing Verification
1.10.4 Testing Facilities
| 1.11 Program Management/SE | 1.11.1 Requirements Compliance
1.11.2 Funds Allocation
| 1.12 Vehicle Design | 1.12.1 Vehicle Frame
1.12.2 Application Software
1.12.3 System Software
1.12.4 Communications
1.12.5 Navigation/Guidance
1.12.6 Central Computer
1.12.7 Fire Control
1.12.8 Data Display and Controls
1.12.9 Survivability
1.12.10 Automatic Handling Control
1.12.11 Auxiliary Equipment
1.12.12 Avionics
| 1.13 HR | 1.13.1 Talent Acquisition
1.13.2 Dispute Resolution
1.13.3 Contracting Negotiation
1.13.4 Policy Iterations